## 2021-2025 RF
2021 - 2025 Results Framework
Outcomes, intervention strategies and main activities | Expected output | Org Responsible | Spending 2021-2025 All Consortium Members | Unit of measure
T: Targets ¦ A: Achievement
[5 empty] | Overall |  | 2025 |  | 2024 |  | 2023 |  | 2022 |  | 2021
Intermediate outcome 1: Strengthened CSOs are inclusive of or led by young women from four rights holder groups, and work together in a CoA to defend and promote their SRH-R.
Regranting |  |  | 5860484.9714 |  | T | A | T | A | T | A | T | A | T | A | T | A
1.1. Setting up and realising the smooth and inspirational functioning of the CoA |  |  | 442099.7982
1.1.1. In nine countries, local organizations have developed individual and/or joint project proposals of good quality. | # and quality of organizational level and joint plans. | Hivos |  | Plans | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 9 | 7 | 0 | 0
1.1.2 In nine countries, participatory assessment panels or other participatory regranting mechanisms are operational. | # of participatory assessment panels or other participatory regranting mechanisms | Hivos |  | Panels | 9 | 9 | 9 | 9 | 9 | 8 | 9 | 6 | 8 | 6 | 9 | 6
1.1.3. Making an accessible overview at country level of capacity strengthening needs and capacity strengthening offers, of local organizations and consortium members. | - Overview of capacity strengthening needs and offers per country available. | Hivos |  | Capacity assessment | 9 | 9 | 9 | 8 | 9 | 9 | 9 | 6 | 9 | 1 | 0 | 0
1.1.5. Trainings and (linking and learning) workshops for CoA facilitators realized, coaching and support structures in place | # CoA facilitators trained (or contracted 2021) | All |  | People | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 9 | 9 | 9 | 8
| # facilitators confident and able to facilitate, support and coordinate CoA meetings | All |  | Outcomes | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 9 | 9 | 9 | 8
1.2 Psychosocial wellbeing and leadership development |  |  | 531859.8856 |  |  |  | 0 | 0 | 0 | 0
1.2.1. COA facilitators engage in leadership development and coaching trajectory | # CoA facilitators and COA members engaged in trajectory | RD |  | People | 39 | 87 | 3 | 5 | 9 | 63 | 9 | 3 | 9 | 9 | 9 | 7
1.2.2. Outreach, engagement and selection process for LILO facilitators | # of people trained on LILO methodologies | PV |  | People | 374 | 413 | 40 | 66 | 18 | 125 | 262 | 164 | 40 | 44 | 14 | 14
1.2.3. Support to COA Facilitators | CoAFs supported to fulfill their role | All |  | People | 9 | 9 | 7 | 7 | 6 | 9 | 9 | 8 | 9 | 9 | 9 | 7
1.2.4. Young women rights holders increasingly take up leadership roles in their organizations, in networks and other joint spaces, and in preparations of (advocacy) events. | # young women rights holders who have a leading role in their organizations, in networks and other joint spaces, and in advocacy events. | RD |  | People | 232 | 229 | 21 | 53 | 81 | 108 | 81 | 53 | 40 | 5 | 9 | 10
1.3 Knowledge, capacities, skills, tools and stronger networks for SRH-R advocacy. |  |  | 465792.7558
1.3.3. Resource development (online and offline) | - Resource developed to support capacity strengthening of COAs | RD/Saatch |  | Resources | 9 | 9 | 1 | 3 | 9 | 9 | 0 | 0 | 9 | 2 | 0 | 0
1.3.4. Work with COA and rights holders to develop key advocacy and campaign messages | # of messages developed | Saatchi |  | Messages | 16 | 11 | 1 | 2 | 4 | 3 | 9 | 3 | 2 | 3 | 0 | 0
1.3.5 Training on oposition monitoring and mitigation during in country training | # of women rights holders trained | Femnet |  | People | 409 | 323 | 28 | 38 | 110 | 88 | 146 | 114 | 125 | 83 | 0 | 0
1.3.7. Train young women rights holders and their organizations on national, regional, and international level SRH-R policies and laws, and know to use tools and methodologies to influence these. | # young women rights holders and their organizations that have been trained. | Femnet |  | People | 726 | 442 | 16 | 35 | 323 | 271 | 262 | 32 | 125 | 104 | 0 | 0
| #/young women rights holders and their organizations that participate in policy and decision-making bodies | Femnet |  | COA organizations | 87 | 71 | 8 | 23 | 38 | 39 | 32 | 4 | 9 | 5 | 0 | 0
1.4 Organisational strengthening |  |  | 834315.1128
1.4.1. M&E refresher training on Outcome harvesting | # of persons trained on Outcome Harvesting | Hivos |  | people | 716 | 510 | 127 | 170 | 147 | 152 | 242 | 80 | 200 | 108 | 0 | 0
1.4.2. Financial independence and resilience training | # /%organizations have increased financial capacities | Hivos |  | organizations | 148 | 209 | 81 | 118 | 22 | 51 | 36 | 40 | 9 | 0 | 0 | 0
1.4.4. In nine countries, organizations have stronger organizational structures (for example financial-administrative and / or decision-making structures and / or PMEL systems) | # organizations engaged in organizational capacity strengthening activities. | All |  | organizations | 464 | 374 | 110 | 102 | 128 | 118 | 136 | 53 | 90 | 101 | 0 | 0
| # changes in organizational structures. | All |  | Changes | 265 | 149 | 77 | 62 | 42 | 59 | 45 | 20 | 101 | 8 | 0 | 0
| Feedback of organizations. | All |  |  | 465 | 258 | 110 | 87 | 119 | 120 | 135 | 51 | 101 | 0 | 0 | 0
1.5 Data and research |  |  | 210145.4152
1.5.1 Research into history and online publication (Women's Achievement Timeline) 'live' and updated current SRH-R movement and leaders | - Research realized and online publication 'live' and updated | RD |  | Pubs | 7 | 15 | 1 | 6 | 1 | 4 | 1 | 0 | 4 | 5 | 0 | 0
1.5.2. Longitudinal studies on the COAs kick off | # Countries participating in Local ownership longitudinal survey | Hivos |  | Studies | 14 | 5 | 4 | 3 | 1 | 0 | 4 | 2 | 5 | 0 | 0 | 0
1.5.3 Rights holders and their organizations engage in training on research and data collection, and are able use this in their advocacy. | # trainings in doing research, gathering data or using this information for SRH-R advocacy. | Hivos |  | Trainings | 26 | 20 | 3 | 3 | 9 | 9 | 9 | 8 | 5 | 0 | 0 | 0
| # of participants in training disaggregated by rights holder group, gender and age | All |  | People | 438 | 500 | 37 | 83 | 266 | 239 | 270 | 134 | 135 | 44 | 0 | 0
1.6 Safety and security, risk and conflict |  |  | 112011.3011 |  |  |  | 0 | 0 | 0 | 0
1.6.1. Developing and agreeing on safety and security procedures, including a monitoring and reporting system, mitigation measures and crisis protocols | Updated - Revised Overarching safety and security procedures, including a monitoring system, mitigation measures, and crisis protocols in place and implemented. | Hivos |  | Protocols | 36 | 29 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 2 | 0 | 0
1.6.2. Space to develop and share safety and security mechanisms to mitigate negative backlash | - Participants aware of safety and security mechanisms and able to use mechanisms on the local level. | All |  | People | 734 | 668 | 184 | 165 | 100 | 130 | 270 | 134 | 180 | 239 | 0 | 0
1.6.3. Fine-tune/ updating of safety and security procedures at the national level, including a monitoring system, mitigation measures, and crisis protocols. | # Safety and security procedures operational at the national level, including a monitoring system, mitigation measures and crisis protocols. | Hivos |  | Protocols | 36 | 33 | 9 | 9 | 9 | 9 | 9 | 5 | 9 | 10 | 0 | 0
1.6.4. Safety and security focal persons are trained and coached | # of trainings and coaching sessions for HO and COAs S&S focal persons | Hivos |  | People | 377 | 352 | 94 | 100 | 130 | 112 | 135 | 129 | 9 | 9 | 9 | 2
1.6.5. Developing and agreeing on overarching risk- and conflict-analysis, monitoring and mitigation procedures | - Overarching risk- and conflict analysis, monitoring and mitigation procedures in place and implemented. | Hivos/All |  | Protocol | 36 | 32 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 5 | 0 | 0
1.6.6. Fine-tune/updating risk- and conflict analysis, monitoring and mitigation procedures at the national level. | # Risk- and conflict analysis, monitoring and mitigation procedures in place and implemented. | All/hivos |  | Protocols | 36 | 29 | 9 | 9 | 9 | 9 | 9 | 8 | 9 | 3 | 0 | 0
1.7 Linking and learning |  |  | 993540.3253
1.7.1. Realizing 'Open' CoA sessions to stimulate cross-over and joint collaborations | # and content of 'Open' CoA sessions | HO |  | Sessions | 83 | 74 | 6 | 6 | 34 | 37 | 34 | 19 | 9 | 12 | 0 | 0
| # of joint initiatives with organizations or actors not funded by We Lead | Hivos |  | Sessions | 78 | 53 | 7 | 7 | 34 | 30 | 34 | 14 | 3 | 2 | 0 | 0
1.7.3. Introducing and linking local organizations to RDs Youth Collective Platform | - Local organizations introduced and linked to Youth Collective Platform | RD |  | Organizations | 289 | 134 | 10 | 39 | 90 | 56 | 90 | 32 | 90 | 0 | 9 | 7
1.7.4. Innovative crossover initiatives on SRH-R advocacy developed and implemented. | # of young women rights holder organizations, outside actors, ‘unusual’ and potential allies participating. | Hivos |  | People | 733 | 624 | 123 | 94 | 280 | 222 | 280 | 308 | 50 | 0 | 0 | 0
| # of innovative, cross-over initiatives on SRH- | Hivos |  | Event | 53 | 42 | 8 | 14 | 18 | 12 | 18 | 16 | 9 | 0 | 0 | 0
| SRHR advocacy developed and implemented. | Hivos |  | Strategies | 37 | 34 | 9 | 7 | 19 | 18 | 9 | 9 | 0 | 0 | 0 | 0
| Quality of collaborations | Hivos |  |  | 0 | 14 |  | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Feedback of participants. | Hivos |  |  | 0 | 13 |  | 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.7.5. Internal learning and feedback sessions within the CoA, to share and discuss project plans, results and bottlenecks. | # of COA-sessions in which plans and results and bottlenecks are shared and discussed. | All |  | Sessions | 139 | 110 | 49 | 45 | 36 | 32 | 36 | 29 | 18 | 4 | 0 | 0
| Global linking and learning forum held | All |  | Outcomes | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Intermediate outcome 2: The general public increasingly acknowledges and supports young women’s SRHR
Regranting |  |  | 5173215.3225
2.1 Safe space dialogues to engage a growing number of supportive allies for rightsholders' SRH-R |  |  | 462181.4024
2.1.3 Create an online platform on which organizations can share information | # of articles on SRH-R of rights holders | ALL |  | Articles | 96 | 61 | 6 | 11 | 36 | 23 | 36 | 22 | 18 | 5 | 0 | 0
2.1.5 Rights holders engage in dialogue with their direct circles, influencers and societal leaders. | # of dialogues and influencing initiatives by rights holders and their organizations | RD |  | Dialogues | 138 | 80 | 1 | 7 | 66 | 56 | 66 | 14 | 5 | 3 | 0 | 0
2.2 Developing communication and campaigning skills of rightholder groups and CSOs |  |  | 215991.4792
2.2.1. Developing communication capacity of the rights holders and their organizations | # of workshops conducted | Hivos/Saatchi/Akahata |  | Sessions | 24 | 19 | 2 | 4 | 4 | 6 | 9 | 9 | 9 | 0 | 0 | 0
2.3 Designing and implementing campaigns |  |  | 170517.9694
2.3.1. Amplifying rights holders voices through various communication platforms | # of publications | Hivos/RD |  | Pubs | 113 | 84 | 29 | 20 | 33 | 23 | 33 | 33 | 18 | 1 | 0 | 7
2.3.2 Rights holders have tools and strategies to implement activities to influence public opinion on SRH-R | # of trainings and coaching-sessions with rights holders | Hivos/Saatchi/Marsa |  | Sessions | 41 | 36 | 5 | 9 | 9 | 6 | 9 | 14 | 18 | 7 | 0 | 0
2.3.3 Rights holders undertake activities to influence public opinion on SRH-R issues | # of influencing initiatives by rights holders and their organizations | Hivos/Saatchi/Marsa |  | Initiatives | 111 | 89 | 24 | 21 | 34 | 22 | 34 | 39 | 19 | 7 | 0 | 0
2.4 Engaging media |  |  | 25747.4012
2.4.1. Reaching out to media; informing them about rights holders’ SRH-R, and connecting to relevant groups and/or events. | # of publications | Hivos/ |  | Pubs | 93 | 120 | 11 | 33 | 34 | 27 | 34 | 38 | 14 | 22 | 0 | 0
2.4.2 Positive messages on rights holders’ SRH-R on (social) media | proportion of positive messages on rights holders’ SRH-R in (social) media | Hivos |  | Messages | 20% | 231% | 5% | 178% | 5% | 35% | 5% | 16% | 5% | 2% | 0 | 0
Intermediate outcome 3: Health-service providers are more aware of the SRH-R needs and situation of rightsholder groups, and increasingly provide accessible, comprehensive, high-quality, inclusive and respectful SRH-R information and services.
Regranting |  |  | 4714929.6825
3.1 Advocacy, dialogue and training with health service staff |  |  | 171725.8169
3.1.1. Train staff from the Ministry of Health on inclusive SRH-R | - Staff of Ministry of Health trains healthcare workers on inclusive SRH-R | COAs/ Marsa |  | People | 632 | 651 | 30 | 55 | 197 | 139 | 200 | 206 | 205 | 251 | 0 | 0
3.1.2. Establishment of national health advocacy champions forum | # of healthcare workers with strengthened capacity | COAs/ Marsa |  | People | 236 | 300 | 0 | 61 | 15 | 6 | 16 | 32 | 205 | 201 | 0 | 0
3.1.3 Rights holders have tools, capacities and skills to engage in dialogue with, create awareness, and train health service providers in issues related to their SRH-R. | # of trainings and coaching-sessions with rights holders | Hivos/ Marsa |  | Sessions | 32 | 24 | 7 | 9 | 8 | 4 | 8 | 11 | 9 | 0 | 0 | 0
| # feedback of rights holders | Hivos/ Marsa |  | Outcomes | 82 | 37 | 9 | 5 | 32 | 16 | 32 | 16 | 9 | 0 | 0 | 0
3.2 Monitoring and research of health service provision |  |  | 417395.1875
3.2.1 Rightsholders and their organisations -with the support of the consortium partners - implement activities to influence health service providers. | Level of CoA appreciation for changes in health service provision (as expressed by award for best clinic & recognition of best practices) | PV/Hivos | 5 - 1 facility per HSMA implementing country | Outcomes | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 |  |  | 0 | 0
3.2.2 Health workers/health facility managers attending Open CoA sessions | # health workers/health facility managers invited to and attending Open CoA sessions | PV/Hivos |  | People | 451 | 374 | 60 | 52 | 163 | 123 | 183 | 146 | 45 | 53 | 0 | 0
3.2.3 Research on SRH-R undertaken | # of researches on SRH-R undertaken with and by rights holders (breakdown by rights holder group) | Hivos/RD |  | Researches | 38 | 24 | 9 | 6 | 9 | 9 | 15 | 2 | 5 | 7 | 0 | 0
| # of rights holders using the available data to improve their access to and the quality of SRH-R information and services (breakdown by rights holder group) | All |  | Rights holders | 263 | 338 | 46 | 66 | 92 | 80 | 125 | 192 | 0 | 0 | 0 | 0
3.3 Lobby to improve accessibility to SRH-R information and services |  |  | 64223.8424
3.3.1. Stimulate creative expressions to enhance advocacy with SRH-R providers | Creative expression to improve SRH-R information and services. | All |  | Outcomes | 80 | 102 | 6 | 5 | 35 | 60 | 36 | 36 | 3 | 1 | 0 | 0
Intermediate outcome 4: Duty-bearers increasingly design, adopt and implement laws and policies that respect and protect the SRH-R of young women from rights holder groups.
Regranting |  |  | 5748991.007
4.1. Local level dialogues and advocacy with duty-bearers to improve laws and policies and / or their implementation |  |  | 460832.6776
4.1.1. Local policy advocacy engagements | # of local advocacy document/ issues developed | All |  | Documents | 46 | 39 | 12 | 17 | 11 | 11 | 14 | 8 | 9 | 3 | 0 | 0
4.1.2 Comprehensive transfer of LILO inclusion methodology to LILO facilitators within COAs | # of workshops conducted | PV |  | Sessions | 44 | 29 | 2 | 0 | 10 | 0 | 9 | 10 | 9 | 5 | 14 | 14
4.1.3 Training and coaching of rights holders to strengthen lobby and advocacy capacities, skills and networks. | # of trainings / coaching with | Saatchi, Femnet |  | Session | 29 | 29 | 2 | 7 | 9 | 4 | 9 | 16 | 9 | 2 | 0 | 0
| # of participants | Saatchi, Femnet |  | People | 630 | 298 | 40 | 80 | 205 | 97 | 250 | 106 | 135 | 15 | 0 | 0
4.2 National level dialogues and advocacy with duty bearers for improved laws and policies and / or their implementation |  |  | 49668.0472
4.2.1. Stimulate creative expressions to enhance SRH-R advocacy to influence duty-bearers | - Creative expression to improve SRH-R information and services. | All |  | Outcomes | 87 | 76 | 6 | 6 | 36 | 57 | 36 | 13 | 9 | 0 | 0 | 0
4.2.2. High level policy dialogue engagements | # of high level policy engagements | All |  | Dialogues sessions | 93 | 76 | 11 | 12 | 32 | 31 | 32 | 28 | 18 | 5 | 0 | 0
4.3 Regional level dialogues and advocacy with duty bearers for improved laws and policies and / or their implementation |  |  | 117412.4083
4.3.1. Stimulate creative expressions to enhance SRH-R advocacy to influence duty-bearers | - Creative expression to improve SRH-R information and services. | All |  | Outcomes | 75 | 75 | 2 | 5 | 32 | 57 | 32 | 13 | 9 | 0 | 0 | 0
4.4 international level dialogues and advocacy with duty bearers for improved laws and policies and / or their implementation |  |  | 124352.8535
4.4.1. Participation in global events to follow up on international commitments (CSW, CPD, among others) | # of recommendations of RH included in policy documents | All |  | Recommendations | 91 | 75 | 12 | 18 | 36 | 38 | 36 | 17 | 7 | 2 | 0 | 0
| # of EPU recommendations on SRHR “aceptados por el estado de Honduras" | Hivos |  | Recommendations | 45 | 35 | 3 | 4 | 34 | 29 | 4 | 0 | 4 | 2 | 0 | 0