## 2025 Results Framework
2025 Costed Workplan
Outcomes, intervention strategies and main activities | Expected output | Org Responsible | Spending 2025 All Consortium Members | Unit of measure |  |  | AFRICA | [9 empty] | MENA |  |  |  | LATAM
T: Targets ¦ A: Achievement
[5 empty] | Overall Target | Overall Achievement | UG |  | KE |  | NG |  | NE |  | MZ |  | LB |  | JO |  | GT |  | HN
Intermediate outcome 1: Strengthened CSOs are inclusive of or led by young women from four rights holder groups, and work together in a CoA to defend and promote their SRH-R.
Regranting |  |  | 935894.2118 |  | T | A | T | A | T | A | T | A | T | A | T | A | T | A | T | A | T | A | T | A
1.1. Setting up and realising the smooth and inspirational functioning of the CoA |  |  | 33150.01
1.1.1. In nine countries, local organizations have developed individual and/or joint project proposals of good quality. | # and quality of organizational level and joint plans. | Hivos |  | Plans | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1.2 In nine countries, participatory assessment panels or other participatory regranting mechanisms are operational. | # of participatory assessment panels or other participatory regranting mechanisms | Hivos |  | Panels | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1.3. Making an accessible overview at country level of capacity strengthening needs and capacity strengthening offers, of local organizations and consortium members. | - Overview of capacity strengthening needs and offers per country available. | Hivos |  | Capacity assessment | 9 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1.5. Trainings and (linking and learning) workshops for CoA facilitators realized, coaching and support structures in place | # CoA facilitators trained | All |  | People | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| # facilitators confident and able to facilitate, support and coordinate CoA meetings | All |  | Outcomes | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.2 Psychosocial wellbeing and leadership development |  |  | 6145.7551 |  | 0
1.2.1. COA facilitators engage in leadership development and coaching trajectory | # CoA facilitators engaged in trajectory | RD |  | People | 3 | 5 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2. Outreach, engagement and selection process for LILO facilitators | # of people trained on LILO methodologies | PV |  | People | 40 | 60 | 10 | 2 | 0 | 0 | 10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 26 | 10 | 19
1.2.3. Support to COA Facilitators | CoAFs supported to fulfill their role | All |  | People | 7 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
1.2.4. Young women rights holders increasingly take up leadership roles in their organizations, in networks and other joint spaces, and in preparations of (advocacy) events. | # young women rights holders who have a leading role in their organizations, in networks and other joint spaces, and in advocacy events. | RD |  | People | 21 | 53 | 0 | 15 | 0 | 12 | 0 | 17 | 6 | 6 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 Knowledge, capacities, skills, tools and stronger networks for SRH-R advocacy. |  |  | 57860.0348 |  | 0
1.3.3. Resource development (online and offline) | - Resource developed to support capacity strengthening of COAs | RD/Saatch |  | Resources | 1 | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.4. Work with COA and rights holders to develop key advocacy and campaign messages | # of messages developed | Saatchi |  | Messages | 1 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5 Training on oposition monitoring and mitigation during in country training | # of women rights holders trained | Femnet |  | People | 28 | 38 | 0 | 2 | 0 | 3 | 16 | 3 | 12 | 2 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.7. Train young women rights holders and their organizations on national, regional, and international level SRH-R policies and laws, and know to use tools and methodologies to influence these. | # young women rights holders and their organizations that have been trained. | Femnet |  | People | 16 | 35 | 0 | 2 | 0 | 2 | 16 | 3 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Femnet |  | COA organizations | 8 | 23 | 0 | 3 | 0 | 4 | 8 | 2 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 Organisational strengthening |  |  | 155156.2134 |  | 0 | 0 | [11 empty] | 0 |  | 0
1.4.1. M&E refresher training on Outcome harvesting | # of persons trained on Outcome Harvesting | Hivos |  | people | 127 | 170 | 36 | 30 | 27 | 25 | 16 | 17 | 12 | 29 | 14 | 17 | 1 | 1 | 1 | 1 | 10 | 25 | 10 | 25
1.4.2. Financial independence and resilience training | # /%organizations have increased financial capacities | Hivos |  | organizations | 81 | 118 | 5 | 15 | 5 | 11 | 8 | 8 | 6 | 6 | 14 | 30 | 17 | 14 | 14 | 14 | 6 | 10 | 6 | 10
1.4.4. In nine countries, organizations have stronger organizational structures (for example financial-administrative and / or decision-making structures and / or PMEL systems) | # organizations engaged in organizational capacity strengthening activities. | All |  | organizations | 110 | 105 | 15 | 15 | 11 | 11 | 8 | 8 | 6 | 6 | 14 | 14 | 17 | 14 | 14 | 14 | 12 | 13 | 13 | 10
| # changes in organizational structures. | All |  | Changes | 77 | 62 | 5 | 5 | 5 | 5 | 5 | 7 | 5 | 6 | 14 | 7 | 17 | 14 | 14 | 14 | 6 | 1 | 6 | 3
| Feedback of organizations. | All |  |  | 110 | 87 | 15 | 9 | 11 | 10 | 8 | 7 | 6 | 6 | 14 | 7 | 17 | 14 | 14 | 14 | 12 | 10 | 13 | 10
1.5 Data and research |  |  | 26882.4038 |  | 0
1.5.1 Research into history and online publication (Women's Achievement Timeline) 'live' and updated current SRH-R movement and leaders | - Research realized and online publication 'live' and updated | RD |  | Pubs | 1 | 6 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.2. Longitudinal studies on the COAs kick off | # Countries participating in Local ownership longitudinal survey | Hivos |  | Studies | 4 | 3 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
1.5.3 Rights holders and their organizations engage in training on research and data collection, and are able use this in their advocacy. | # trainings in doing research, gathering data or using this information for SRH-R advocacy. | Hivos |  | Trainings | 3 | 4 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0
| # of participants in training disaggregated by rights holder group, gender and age | All |  | People | 37 | 108 | 9 | 12 | 0 | 12 | 3 | 17 | 0 | 0 | 0 | 0 | 0 | 12 | 22 | 0 | 3 | 40 | 0 | 15
1.6 Safety and security, risk and conflict |  |  | 12820.06 |  | 0
1.6.1. Developing and agreeing on safety and security procedures, including a monitoring and reporting system, mitigation measures and crisis protocols | Updated - Revised Overarching safety and security procedures, including a monitoring system, mitigation measures, and crisis protocols in place and implemented. | Hivos |  | Protocols | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.6.2. Space to develop and share safety and security mechanisms to mitigate negative backlash | - Participants aware of safety and security mechanisms and able to use mechanisms on the local level. | All |  | People | 184 | 165 | 36 | 18 | 27 | 20 | 16 | 17 | 12 | 12 | 10 | 30 | 18 | 14 | 15 | 14 | 24 | 20 | 26 | 20
1.6.3. Fine-tune/ updating of safety and security procedures at the national level, including a monitoring system, mitigation measures, and crisis protocols. | # Safety and security procedures operational at the national level, including a monitoring system, mitigation measures and crisis protocols. | Hivos |  | Protocols | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.6.4. Safety and security focal persons are trained and coached | # of trainings and coaching sessions for HO and COAs S&S focal persons | Hivos |  | People | 94 | 100 | 15 | 15 | 11 | 11 | 8 | 8 | 6 | 6 | 2 | 18 | 1 | 1 | 1 | 1 | 24 | 20 | 26 | 20
1.6.5. Developing and agreeing on overarching risk- and conflict-analysis, monitoring and mitigation procedures | - Overarching risk- and conflict analysis, monitoring and mitigation procedures in place and implemented. | Hivos/All |  | Protocol | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.6.6. Fine-tune/updating risk- and conflict analysis, monitoring and mitigation procedures at the national level. | # Risk- and conflict analysis, monitoring and mitigation procedures in place and implemented. | All/hivos |  | Protocols | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.7 Linking and learning |  |  | 250031.8956 |  | 0
1.7.1. Realizing 'Open' CoA sessions to stimulate cross-over and joint collaborations | # and content of 'Open' CoA sessions | HO |  | Sessions | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| # of joint initiatives with organizations or actors not funded by We Lead | Hivos |  | Sessions | 7 | 7 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
1.7.3. Introducing and linking local organizations to RDs Youth Collective Platform | - Local organizations introduced and linked to Youth Collective Platform | RD |  | Organizations | 10 | 39 |  | 15 |  | 11 |  | 8 |  | 0 | 10 | 5 |  | 0 |  | 0 |  | 0 |  | 0
1.7.4. Innovative crossover initiatives on SRH-R advocacy developed and implemented. | # of young women rights holder organizations, outside actors, ‘unusual’ and potential allies participating. | Hivos |  | People | 123 | 94 | 20 | 11 | 20 | 14 | 16 | 16 | 12 | 1 | 30 | 32 | 0 | 0 | 0 | 0 | 12 | 10 | 13 | 10
| # of innovative, cross-over initiatives on SRH- | Hivos |  | Event | 8 | 14 | 1 | 3 | 1 | 2 | 2 | 4 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| SRHR advocacy developed and implemented. | Hivos |  | Strategies | 9 | 7 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Quality of collaborations | Hivos |  |  |  | 14 |  | 3 |  | 4 |  | 6 |  |  |  | 1
| Feedback of participants. | Hivos |  |  |  | 13 |  | 3 |  | 4 |  | 6 |  |  |  | 0
1.7.5. Internal learning and feedback sessions within the CoA, to share and discuss project plans, results and bottlenecks. | # of COA-sessions in which plans and results and bottlenecks are shared and discussed. | All |  | Sessions | 49 | 45 | 2 | 2 | 2 | 2 | 6 | 6 | 3 | 2 | 3 | 1 | 17 | 14 | 14 | 14 | 1 | 2 | 1 | 2
| Global linking and learning forum held | All |  | Outcomes/ People | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Intermediate outcome 2: The general public increasingly acknowledges and supports young women’s SRHR
Regranting |  |  | 600674.635
2.1 Safe space dialogues to engage a growing number of supportive allies for rightsholders' SRH-R |  |  | 42784.0691
2.1.3 Create an online platform on which organizations can share information | # of articles on SRH-R of rights holders | ALL |  | Articles | 6 | 11 | 0 | 2 | 0 | 2 | 1 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
2.1.5 Rights holders engage in dialogue with their direct circles, influencers and societal leaders. | # of dialogues and influencing initiatives by rights holders and their organizations | RD |  | Dialogues | 1 | 7 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 Developing communication and campaigning skills of rightholder groups and CSOs |  |  | 85704.5817
2.2.1. Developing communication capacity of the rights holders and their organizations | # of workshops conducted | Hivos/Saatchi/Akahata |  | Sessions | 2 | 4 | 1 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 Designing and implementing campaigns |  |  | 50814.0738
2.3.1. Amplifying rights holders voices through various communication platforms | # of publications | Hivos/RD |  | Pubs | 29 | 20 | 2 | 4 | 2 | 5 | 4 | 4 | 1 | 0 | 4 | 3 | 5 | 0 | 5 | 0 | 3 | 2 | 3 | 2
2.3.2 Rights holders have tools and strategies to implement activities to influence public opinion on SRH-R | # of trainings and coaching-sessions with rights holders | Hivos/Saatchi/Marsa |  | Sessions | 5 | 9 | 1 | 2 | 1 | 2 | 0 | 3 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
2.3.3 Rights holders undertake activities to influence public opinion on SRH-R issues | # of influencing initiatives by rights holders and their organizations | Hivos/Saatchi/Marsa |  | Initiatives | 24 | 21 | 2 | 5 | 2 | 3 | 4 | 3 | 5 | 2 | 4 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 1
2.4 Engaging media |  |  | 2977.62
2.4.1. Reaching out to media; informing them about rights holders’ SRH-R, and connecting to relevant groups and/or events. | # of publications | Hivos/ |  | Pubs | 11 | 33 | 2 | 4 | 2 | 5 | 2 | 20 | 0 | 0 | 3 | 0 | 0 |  | 0 |  | 1 | 2 | 1 | 2
2.4.2 Positive messages on rights holders’ SRH-R on (social) media | proportion of positive messages on rights holders’ SRH-R in (social) media | Hivos |  | Messages | 5% | 178% | 5% | 5% | 5% | 5% |  | 98% |  |  | 10% | 60% | 0% |  | 0% |  | 5% | 5% | 5% | 5%
Intermediate outcome 3: Health-service providers are more aware of the SRH-R needs and situation of rightsholder groups, and increasingly provide accessible, comprehensive, high-quality, inclusive and respectful SRH-R information and services.
Regranting |  |  | 528528.015
3.1 Advocacy, dialogue and training with health service staff |  |  | 14821.9178
3.1.1. Train staff from the Ministry of Health on inclusive SRH-R | - Staff of Ministry of Health trains healthcare workers on inclusive SRH-R | COAs/ Marsa |  | People | 30 | 55 | 0 | 2 | 0 | 3 | 10 | 10 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 10 | 20 | 10 | 20
3.1.2. Establishment of national health advocacy champions forum | # of healthcare workers with strengthened capacity | COAs/ Marsa |  | People | 0 | 61 | 0 | 15 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 9 | 0 | 0 | 0 | 0
3.1.3 Rights holders have tools, capacities and skills to engage in dialogue with, create awareness, and train health service providers in issues related to their SRH-R. | # of trainings and coaching-sessions with rights holders | Hivos/ Marsa |  | Sessions | 7 | 9 | 1 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 0 |  | 1 | 1 | 1 | 1
| # feedback of rights holders | Hivos/ Marsa |  | Outcomes | 9 | 5 | 2 | 1 | 2 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1
3.2 Monitoring and research of health service provision |  |  | 67724.8271
Rightsholders and their organisations -with the support of the consortium partners - implement activities to influence health service providers. | Level of CoA appreciation for changes in health service provision (as expressed by award for best clinic & recognition of best practices) | PV/Hivos |  | Outcomes | 5 - 1 facility per HSMA implementing country | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
3.2.2 Health workers/health facility managers attending Open CoA sessions | # health workers/health facility managers invited to and attending Open CoA sessions | PV/Hivos |  | People | 60 | 52 | 25 | 7 | 20 | 5 | 10 | 20 | 5 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.3 Research on SRH-R undertaken | # of researches on SRH-R undertaken with and by rights holders (breakdown by rights holder group) | Hivos/RD |  | Researches | 9 | 6 | 3 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| # /% of rights holders using the available data to improve their access to and the quality of SRH-R information and services | All |  | Rights holders | 46 | 66 | 15 | 9 | 11 | 7 | 20 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0
3.3 Lobby to improve accessibility to SRH-R information and services |  |  | 4093.53
3.3.1. Stimulate creative expressions to enhance advocacy with SRH-R providers | Creative expression to improve SRH-R information and services. | All |  | Outcomes | 6 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Intermediate outcome 4: Duty-bearers increasingly design, adopt and implement laws and policies that respect and protect the SRH-R of young women from rights holder groups.
Regranting |  |  | 688983.618
4.1. Local level dialogues and advocacy with duty-bearers to improve laws and policies and / or their implementation |  |  | 23405.8798
4.1.1. Local policy advocacy engagements | # of local advocacy document/ issues developed | All |  | Documents | 12 | 17 | 1 | 1 | 1 | 2 | 2 | 5 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
4.1.2 Comprehensive transfer of LILO inclusion methodology to LILO facilitators within COAs | # of workshops conducted | PV |  | Sessions | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.3 Training and coaching of rights holders to strengthen lobby and advocacy capacities, skills and networks. | # of trainings / coaching with | Saatchi, Femnet |  | Session | 2 | 7 | 1 | 1 | 1 | 1 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| # of participants | Saatchi, Femnet |  | People | 40 | 80 | 25 | 20 | 15 | 15 |  | 15 |  | 0 |  | 30 |  |  |  |  | 0 | 0 | 0 | 0
4.2 National level dialogues and advocacy with duty bearers for improved laws and policies and / or their implementation |  |  | 9274.8064 |  | 0
4.2.1. Stimulate creative expressions to enhance SRH-R advocacy to influence duty-bearers | - Creative expression to improve SRH-R information and services. | All |  | Outcomes | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
4.2.2. High level policy dialogue engagements | # of high level policy engagements | All |  | Dialogues sessions | 11 | 12 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2
4.3 Regional level dialogues and advocacy with duty bearers for improved laws and policies and / or their implementation |  |  | 14091.038 |  | 0
4.3.1. Stimulate creative expressions to enhance SRH-R advocacy to influence duty-bearers | - Creative expression to improve SRH-R information and services. | All |  | Outcomes | 2 | 5 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 international level dialogues and advocacy with duty bearers for improved laws and policies and / or their implementation |  |  | 8941.5283 |  | 0
4.4.1. Participation in global events to follow up on international commitments (CSW, CPD, among others) | # of recommendations of RH included in policy documents | All |  | Recommendations | 12 | 18 | 1 | 1 | 1 | 6 | 0 | 2 | 0 | 0 | 4 | 3 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2
| # of EPU recommendations on SRHR “aceptados por el estado de Honduras" | Hivos |  | Recommendations | 3 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2
Note on D71: ====== ID#AAAB1_CDc6A Caili F (2026-03-17 18:35:20) We reported healthcare workers through our HSMA work - is that not included here?